## Assumptions
id | assumption | classification | source_or_basis | owner | impact_if_wrong | how_to_confirm | linked_question | status
A-001 | Founders and developers are in India; an Indian private limited company will be registered | Source-stated | Founder answer | Founder | Governing law; tax; payment gateways; compliance register all change | Founder answer | Q-F01 | Confirmed by founder 2026-10-29 (DEC-022)
A-002 | Founders can spend ₹5,000 to ₹10,000 a month before funding | Source-stated | Founder answer | Founder | GPU capacity for beta must come from credits; beta size limited | Founder answer | Q-F02 | Confirmed by founder 2026-10-29 (DEC-023)
A-003 | January 2027 means a closed beta; final plan set by testing and bug fixes | Source-stated | Founder answer | Founder | Roadmap and scrum plan compress; quality and stability risk | Founder answer | Q-F03 | Confirmed by founder 2026-10-29 (DEC-024)
A-004 | Launching on open-weight models with unverifiable training data is acceptable with disclosure | Assumption | Default for Q-F04 | Founder | Model strategy must change to paid licensed API (higher cost) | Founder answer | Q-F04 | Open
A-005 | Free users may commercially use 5 songs per calendar month with attribution | Source-stated | Founder answer | Founder | Free-tier economics and abuse controls change | Founder answer | Q-F05 | Confirmed by founder 2026-10-29 (DEC-025)
A-010 | Each developer works 30 to 50 hours a week; plans use 30 | Source-stated | Founder answer | Founder | Sprint capacity and dates change | Founder answer | Q-F06 | Confirmed by founder 2026-10-29 (DEC-026)
A-020 | ACE-Step 1.5 weights are under a permissive licence (MIT per model card; Apache-2.0 per a secondary source) allowing commercial use of outputs | Source-stated | SRC-106; SRC-107 | Engineering | Model must be replaced | Read LICENSE file in official repo and archive copy (C-02) |  | Open
A-021 | ACE-Step 1.5 handles Hindi and Hinglish lyrics at usable quality | Hypothesis | Model card claims 50+ languages for prompt adherence (SRC-106); Hindi not specifically confirmed | Engineering | Beachhead language strategy fails; fall back to Lyria 3 API for Hindi | Language quality gate G1 |  | Open
A-022 | Stripe does not operate in Pakistan | Assumption | Analyst knowledge; not checked in this batch | Finance | Wave 2 payment plan changes | Check Stripe global availability page (C-04) |  | Open
A-023 | International card payments and Stripe are unavailable inside Russia because of sanctions | Assumption | Analyst knowledge; not checked in this batch | Finance | Russia paid launch plan changes | Check provider country lists (C-04) |  | Open
A-024 | ACE-Step 1.5 training data is licensed; royalty-free; public domain or synthetic as the publisher states | Source-stated | SRC-106 | Legal | Infringement exposure (RISK-001) is higher than modelled | Request data statement from publisher; legal review | Q-F04 | Open
A-025 | ACE-Step 1.5 runs with under 4 GB VRAM and generates a full song in under 10 seconds on an RTX 3090 | Source-stated | SRC-106 | Engineering | Cost model and latency targets change | Benchmark in Sprint 1 on our hardware |  | Open
A-026 | Consumer-grade rented GPUs cost roughly US$0.20 to US$0.50 per hour on marketplace providers | Estimate | Analyst estimate; not checked in this batch | Finance | Cost per song changes | Collect quotes in Batch 4 (C-03) |  | Open
A-027 | Google Lyria 3 Pro API costs about US$0.08 per song and its terms allow commercial use of outputs by our users | Externally sourced (price); Assumption (terms) | SRC-115 | Legal | Fallback path unavailable or dearer | Read Google API terms (C-02) |  | Open
A-028 | Stable Audio 3.0 Small and Medium are free for organisations under US$1M annual revenue and trained on licensed data | Externally sourced | SRC-108 | Legal | Instrumental component must change | Read Stability Community License (C-02) |  | Open
A-029 | Cloudflare R2 has a free tier with no egress fees suitable for audio delivery | Assumption | Analyst knowledge; not checked in this batch | Engineering | Storage and delivery cost rises | Check provider pricing page (C-03) |  | Open
A-030 | Oracle Cloud Always Free ARM instances are available in an Indian region and sufficient for the API in beta | Assumption | Analyst knowledge; not checked in this batch | Engineering | Hosting moves to a paid VM earlier | Check provider pricing page (C-03) |  | Open
A-031 | Startup credit programmes (Google; AWS; Microsoft; NVIDIA) will approve BeatMind once an MVP exists | Assumption | SRC-110 shows Start tier needs a working MVP | Founder | No free GPU capacity; beta must be smaller or paid | Apply after MVP demo | Q-F02 | Open
A-032 | Spotify country prices are a reasonable proxy for local willingness to pay for audio subscriptions | Assumption | SRC-116 | Product | Price bands mis-set | Price test on waitlist (H-004) |  | Open
A-033 | Paid users will accept fair-use rate limits instead of hard download caps | Hypothesis | SRC-002 assumption carried forward | Product | Higher abuse or cost | Beta usage data |  | Open
A-034 | Distributors accept AI-disclosed tracks from Indian users | Assumption | SRC-002 A-04 carried forward | Partnerships | Release workflow value drops | Check distributor policies (C-05) |  | Open
A-035 | The US Copyright Office position of 2025-01-29 still applies and India treats human contribution similarly | Externally sourced (US); Unknown (India) | SRC-120; SRC-102 | Legal | Authorship report value changes | Counsel review per market |  | Open

## Risks
id | risk | category | likelihood | impact | score | mitigation | owner | trigger_to_watch | status | source
RISK-001 | Open-weight model training data cannot be verified; outputs could resemble copyrighted works and expose users and BeatMind to claims | Legal | Medium | High | High | Prefer models with a published data statement (ADR-007); similarity screening before delivery; takedown process; disclose risk in terms and to investors; move to licensed data after funding | Founder and Legal | A rights-holder claim or a court ruling against the model publisher | Open | SRC-101; SRC-106
RISK-002 | Google Lyria 3 already supports Hindi and reaches Indian users through Gemini and YouTube | Market | High | High | High | Compete on price; ownership; downloads; creator workflow and regional languages; do not compete on raw quality | Founder | Google consumer pricing or YouTube integration in India | Open | SRC-112; SRC-113
RISK-003 | Open models do not reach acceptable quality in Hindi and regional languages | Technical | Medium | High | High | Language quality gate G1 before beta; Lyria 3 API fallback for failing languages; publish only passing languages | Engineering | G1 blind-test results | Open | A-021
RISK-004 | No free production GPU capacity; inference cost before funding | Financial | High | Medium | High | Smallest viable model; scale-to-zero GPU workers; credit programmes; invite-only beta with daily caps | Founder | Credit applications declined | Open | A-002; A-031
RISK-005 | January 2027 target is not achievable for a stable public launch | Delivery | High | High | High | Treat January 2027 as demo and closed beta (A-003); cut scope to the MVP list | Scrum Master | Sprint velocity in first two sprints | Open | DEC-007
RISK-006 | Voice cloning or artist imitation misuse | Abuse | Medium | High | High | No voice cloning in Phase 1; block artist names in prompts; impersonation reporting | Product | Abuse reports | Open | SRC-005
RISK-007 | Watermark or provenance stripped; failure to meet India IT Rules and EU Article 50 marking duties | Compliance | Medium | High | High | C2PA manifest plus inaudible watermark plus server-side ledger; label in UI and metadata; test robustness | Engineering | Regulator guidance or failed robustness test | Open | SRC-117; SRC-119
RISK-008 | Free-tier abuse (bulk generation; spam uploads to streaming services) | Abuse | High | Medium | High | Daily generation caps; device and payment fingerprinting; attribution on free songs; per-account limits | Engineering | Generation spikes from new accounts | Open | DEC-008
RISK-009 | Single points of failure on free-tier hosting cause outages | Operational | Medium | Medium | Medium | Stateless services; managed Postgres with backups; queue-based workers; status page; documented migration path to paid cloud | Engineering | Free-tier limit warnings | Open | DEC-014
RISK-010 | Three-person team is overloaded; key-person dependency | Delivery | High | Medium | High | Narrow MVP; automation; documentation; shared ownership of components | Founder | Missed sprint goals | Open | DEC-006
RISK-011 | Rights promise to users conflicts with model licences or law (purely AI output may not be copyrightable) | Legal | Medium | High | High | Promise transfer of whatever rights BeatMind holds; never promise copyright protection; counsel review | Legal | Counsel review | Open | SRC-120; DEC-009
RISK-012 | Russian-language demand cannot be monetised inside Russia because of sanctions and payment restrictions | Market | High | Low | Medium | Support Russian language for users outside Russia; no paid launch in Russia | Founder | Change in sanctions | Open | A-023
RISK-013 | Low willingness to pay in India keeps revenue per user low | Financial | High | Medium | High | Purchasing-power price bands; annual plans; UPI; creator-focused value; international English users at higher bands | Founder | Waitlist price test | Open | SRC-109
RISK-014 | Personal data obligations under India DPDP Act and Rules phase in during 2026-2027 | Compliance | Medium | Medium | Medium | Privacy by design; consent records; retention limits; breach process; DPIA in Batch 2 | Legal | Gazette phase dates (C-07) | Open | SRC-118
RISK-015 | Competitors sign label licences and set licensed training as the market norm; unlicensed models lose distributor acceptance | Market | Medium | High | High | Track distributor policies; prepare licensed-data plan for post-funding | Founder | Distributor policy change | Open | SRC-101

## Sources
id | title | publisher | url | published | accessed | evidence_type | used_for
SRC-001 | Suno teardown and market gap research | BeatMind (internal) | https://claude.ai/artifact/2U93tAK7aEDgAVQmpBYXai | 2026-10-22 | 2026-10-28 | Internal | Competitor features
SRC-002 | BeatMind AI Product Requirements Document v1.0 | BeatMind (internal) | https://claude.ai/artifact/4a7ikpB6JZHiiWm9BF5gXs | 2026-10-22 | 2026-10-28 | Internal | Superseded by PRD v2.0
SRC-003 | BeatMind AI Technical Design Document v1.0 | BeatMind (internal) | https://claude.ai/artifact/4GGrrX1g1qXPBedJKn7cvE | 2026-10-22 | 2026-10-28 | Internal | Superseded by TDD v2.0
SRC-004 | BeatMind AI Pitch Deck (pptx) | BeatMind (internal) | project file | 2026-10-25 | 2026-10-28 | Internal | Claims to rewrite in Batch 4
SRC-005 | BeatMind pre-launch review | BeatMind (internal) | https://claude.ai/artifact/DENoaz2HGQ5nqWYzXtQ6Zv | 2026-10-28 | 2026-10-28 | Internal | Backlog findings
SRC-006 | BeatMind package: open questions and assumptions | BeatMind (internal) | https://claude.ai/artifact/SUeHaYNyFQSHWGH3acvMC2 | 2026-10-28 | 2026-10-28 | Internal | Question baseline
SRC-007 | Founder answers to open questions | Amit Kumar Singh | project thread | 2026-10-28 | 2026-10-28 | Internal | Decision log
SRC-100 | 10 quick (and crucial) takeaways from IFPI's Global Music Report 2026 | Music Business Worldwide | https://musicbusinessworldwide.com/10-quick-and-crucial-takeaways-from-ifpis-global-music-report-2026 | 2026 (undated page) | 2026-10-28 | Externally sourced | Global market size and regional growth
SRC-101 | After Universal, Warner, and Merlin deals, now Udio inks licensing agreement with Kobalt | Music Business Worldwide | https://www.musicbusinessworldwide.com/after-universal-warner-and-merlin-deals-now-udio-inks-licensing-agreement-with-kobalt | 2026-04-09 | 2026-10-28 | Externally sourced | Competitor licensing status
SRC-102 | DPIIT Reviews Copyright Rules for Generative AI Training | Taxmann | https://www.taxmann.com/post/blog/dpiit-reviews-copyright-rules-for-generative-ai-training | 2025-12-11 (updated 2026-09-01) | 2026-10-28 | Externally sourced | India copyright and AI training
SRC-103 | AI Music Statistics 2026 | Dynamoi | https://dynamoi.com/learn/statistics/ai-music-statistics-2026 | 2026-04-26 | 2026-10-28 | Externally sourced (many figures unattributed) | Illustrative only; not used for sizing
SRC-104 | Best Open-Source AI Music Generator 2026 | IT-JIM | https://www.it-jim.com/blog/best-open-source-ai-music-generator/ | 2026-05-21 | 2026-10-28 | Externally sourced | Open model licences
SRC-105 | HeartMuLa heartlib repository | HeartMuLa (MuLa Labs) | https://github.com/HeartMuLa/heartlib | 2026-01-14 onward | 2026-10-28 | Source-stated | Model licence and capability
SRC-106 | ACE-Step 1.5 model card | ACE-Step (StepFun and ACE Studio) | https://huggingface.co/ACE-Step/Ace-Step1.5 | 2026-02 | 2026-10-28 | Source-stated | Model licence and training data claim
SRC-107 | ACE-Step 1.5 overview | ComfyUI Wiki | https://comfyui-wiki.com/en/models/ace-step/ace-step-v1-5 | 2026 | 2026-10-28 | Externally sourced | Model variants (licence differs from SRC-106; see A-020)
SRC-108 | Stability AI launches Stable Audio 3.0 with open weights | The Decoder | https://the-decoder.com/stability-ai-launches-stable-audio-3-0-with-up-to-six-minute-tracks-and-open-weights/ | 2026-05-20 | 2026-10-28 | Externally sourced | Model licence and training data claim
SRC-109 | India's paid music subscriptions could reach 28-30 million by 2028 (EY-IMI) | EY India | https://www.ey.com/en_in/newsroom/2026/07/india-s-paid-music-subscriptions-could-reach-28-30-million-by-2028-as-industry-focuses-on-monetization-and-premium-experiences | 2026-07-24 | 2026-10-28 | Externally sourced | India demand and willingness to pay
SRC-110 | Google for Startups Cloud Program FAQ | Google Cloud | https://cloud.google.com/startup/faq | 2026 (undated) | 2026-10-28 | Source-stated | Startup credit eligibility
SRC-111 | Suno global prices | OpenTheRank | https://opentherank.com/hi/ai-pricing/suno/ | 2026-10-28 | 2026-10-28 | Externally sourced | Competitor regional pricing
SRC-112 | 6 best AI music generation tools for musicians in India in 2026 | Free Press Journal | https://www.freepressjournal.in/tech/6-best-ai-music-generation-tools-for-musicians-in-india-in-2026 | 2026-07-13 | 2026-10-28 | Externally sourced | India competitor landscape and Hindi support
SRC-113 | Google expands ProducerAI into Labs with Lyria 3 | Storyboard18 | https://storyboard18.com/amp/digital/google-expands-producerai-into-labs-with-lyria-3-to-power-end-to-end-ai-music-creation-90859.htm | 2026-02-28 | 2026-10-28 | Externally sourced | Competitor (Google)
SRC-114 | 30+ YouTube Statistics that You Must Know in 2026 | SocialPilot (citing Statista and DataReportal) | https://www.socialpilot.co/youtube-marketing/youtube-statistics | 2026-09-29 | 2026-10-28 | Externally sourced (secondary) | YouTube audience by country
SRC-115 | AI music APIs compared: Mureka vs MiniMax vs ElevenLabs vs Lyria 3 Pro | DEV Community (useapi) | https://dev.to/useapi/ai-music-apis-compared-mureka-vs-minimax-vs-elevenlabs-vs-lyria-3-pro-2kcn | 2026-07-17 (updated 2026-10-28) | 2026-10-28 | Externally sourced | API fallback pricing
SRC-116 | Spotify plans around the world | Selectra | https://selectra.com.au/streaming/providers/spotify-plans-around-the-world | 2025-2026 (mixed) | 2026-10-28 | Externally sourced | Purchasing-power price anchors
SRC-117 | India introduces mandatory labelling for AI and 3-hour takedown for illegal content | Hogan Lovells | https://www.hlc.com/en/publications/india-introduces-mandatory-labelling-for-ai-and-3hour-takedown-for-illegal-content | 2026-02-13 | 2026-10-28 | Externally sourced (law firm) | India IT Rules 2026
SRC-118 | Centre notifies DPDP Rules; implementation in phases over 12-18 months | Deccan Herald | https://www.deccanherald.com/amp/story/india%2Fcentre-notifies-dpdp-rules-implementation-planned-in-phases-spread-over-12-18-months-3798465 | 2025-11-14 | 2026-10-28 | Externally sourced | India data protection
SRC-119 | EU AI Act Article 50: Transparency Obligations Take Effect | Cloud Security Alliance | https://labs.cloudsecurityalliance.org/research/csa-research-note-eu-ai-act-article-50-transparency-20260729/ | 2026-07-29 | 2026-10-28 | Externally sourced | EU AI transparency duties
SRC-120 | US Copyright Office releases Part 2 of AI report | Akin Gump | https://www.akingump.com/en/insights/ai-law-and-regulation-tracker/us-copyright-office-releases-part-2-of-ai-report | 2025-01-29 | 2026-10-28 | Externally sourced (law firm) | Copyrightability of AI output
SRC-121 | RDAP domain lookups (.com) for candidate names | Verisign RDAP | https://rdap.verisign.com/com/v1/domain/ | 2026-10-28 | 2026-10-28 | Verified | Domain availability

## Launch markets
market | audience | ability_to_pay | competitive_gap | model_language_fit | regulatory | payments | founder_proximity | weighted_score
India | 5 | 2 | 5 | 3 | 3 | 4 | 5
United States | 4 | 5 | 2 | 5 | 3 | 4 | 1
Brazil | 4 | 3 | 3 | 3 | 3 | 3 | 1
France and EU | 3 | 5 | 2 | 4 | 2 | 4 | 1
Indonesia | 4 | 2 | 4 | 2 | 3 | 3 | 1
Pakistan, Bangladesh, Nepal | 3 | 1 | 5 | 2 | 2 | 1 | 2
Russia | 3 | 2 | 3 | 4 | 1 | 1 | 1
weight | 0.2 | 0.15 | 0.2 | 0.1 | 0.1 | 0.1 | 0.15

## Review findings
id | review_ref | finding | review_severity | status_after_v2 | resolution_or_next_step | linked_items
BUG-001 | C1 | Free-plan download rule conflicts across documents | High | Resolved | Founder decision DEC-008: MP3 for personal use plus 5 commercial songs a month | REQ-F-20; REQ-F-21
BUG-002 | C2 | Hum input entitlement on Free | Medium | Deferred | Melody input moved to Phase 2 | FEAT-25
BUG-003 | C3 | MIDI entitlement by plan | High | Deferred | MIDI export moved to Phase 2 | FEAT-26
BUG-004 | C4 | Stem count by plan | High | Resolved | 4 separated stems on paid plans | REQ-F-23; entitlement-matrix.csv
BUG-005 | C5 | Stem taxonomy conflicts | Launch-blocking | Resolved | Stem set fixed by the separation model: vocals; drums; bass; other | REQ-F-23; TDD 3
BUG-006 | C6 | Native versus separated stems claim | Launch-blocking | Resolved | Stems are separated after generation and described that way; deck rewrite must not claim native stems | FEAT-07; Batch 4 deck
BUG-007 | C7 | Deck shows lock accuracy that was never measured | High | Open | Measure BPM and key adherence of the model; publish targets only after measurement | TC-REQ-F-04-02
BUG-008 | C8 | Content ID safelist tier conflict | Medium | Resolved | Safelist dropped; replaced by certificate and dispute pack | FEAT-11
BUG-009 | C9 | Content ID safelist marketed as shipped | Launch-blocking | Resolved | No claim-clearance promise anywhere (REQ-F-26) | FEAT-11; REQ-F-26
BUG-010 | C10 | Ownership wording versus deliverable rights | Launch-blocking | Partly resolved | DEC-009 sets user ownership of whatever rights BeatMind holds; certificate wording needs counsel sign-off | REQ-F-22; REQ-F-26; Batch 4 legal pack
BUG-011 | C11 | Song length by plan | Low | Resolved | 30 s to 4 min for all plans in MVP | REQ-F-06
BUG-012 | C12 | Studio plan timing | Medium | Resolved | Studio is Phase 2 | PRD 9
BUG-013 | C13 | Prices missing in deck | Medium | Open | Price bands in Batch 4 financial model | PRD 9; Batch 4
BUG-014 | C14 | Launch wedge conflict | Medium | Resolved | Creators first; then artists; then producers | DEC-102
BUG-015 | C15 | API timing conflict | Low | Resolved | Public API is Phase 3 | FEAT-32
BUG-016 | C16 | Two latency definitions | Low | Resolved | Single SLO: song playable within 60 s at p95 in beta | REQ-NFR-01
BUG-017 | C17 | Voice verification called identity check | High | Deferred | Voice models removed from MVP | FEAT-30
BUG-018 | C18 | Training data under licence only claim | High | Open | Claim must not appear; disclose open-model data risk | RISK-001; A-024
BUG-019 | F1.1 | Rendered audio not verified against locks | High | Open | Post-generation check of tempo and key; retry or label mismatch | TC-REQ-F-04-02
BUG-020 | F1.2 | No rule for conflicting inputs | Medium | Open | Input validation rules in API-001 | REQ-F-04
BUG-021 | F1.3 | Limited meters; no tempo or key changes | Medium | Deferred | Out of MVP scope | Phase 2 backlog
BUG-022 | F1.4 | No Unicode normalisation or injection rules for prompts and lyrics | High | Open | NFC normalisation; strip zero-width and confusables before checks; prompt-injection guard for the lyric model | REQ-SEC-04
BUG-023 | F1.5 | Lyric model may reproduce copyrighted lyrics | High | Open | Lyric similarity check against known lyrics where a lawful index exists; refuse known titles; log | REQ-F-52; TD-03
BUG-024 | F2.1 | No failure states for poor hum recordings | High | Deferred | Hum input is Phase 2 | FEAT-25
BUG-025 | F2.2 | Transcription flattens Indian ornamentation | High | Deferred | Hum input is Phase 2 | FEAT-25
BUG-026 | F2.3 | Uploaded media parsed without sandboxing | High | Deferred | No uploads in MVP; sandbox required when added | FEAT-21; FEAT-25
BUG-027 | F2.4 | Hummed copyrighted melody logged as human input | Launch-blocking | Deferred | Hum input is Phase 2 | FEAT-25
BUG-028 | F3.1 | No refund rules for failed or withheld takes | High | Open | Automatic credit refund for failed; timed-out or withheld takes | REQ-F-56
BUG-029 | F3.2 | Final render may not sound like chosen draft | Launch-blocking | Resolved | MVP generates full takes with one model; no separate render | FEAT-05; TDD 3
BUG-030 | F3.3 | Account farming of free generation | High | Open | Turnstile; device and payment fingerprints; daily caps; phone verification for free commercial licences | RISK-008; REQ-SEC-09
BUG-031 | F3.4 | No concurrency limit per user | Medium | Open | Per-user concurrent job limit by plan | REQ-F-55
BUG-032 | F4.1 | No measurable seam quality test | High | Open | Seam test with onset and spectral discontinuity thresholds | TC-REQ-F-10-02
BUG-033 | F4.2 | Edits re-screen the whole take | Medium | Open | Screen only changed regions plus a context window | TDD 3
BUG-034 | F4.3 | Unbounded take storage | Medium | Open | Per-plan storage quota and take limit per song | entitlement-matrix.csv
BUG-035 | F4.4 | Lyric-line edit syllable changes | Medium | Deferred | Lyric-line edit not in MVP | Phase 2 backlog
BUG-036 | F5.1 | Native stems unproven | Launch-blocking | Resolved | Separated stems only | FEAT-07
BUG-037 | F5.2 | Stem groups cannot produce eight named stems | Launch-blocking | Resolved | Four stems | REQ-F-23
BUG-038 | F5.3 | MIDI may not match audio | High | Deferred | MIDI in Phase 2 | FEAT-26
BUG-039 | F5.4 | Stem bleed not measured | Medium | Open | Disclose that separated stems can contain bleed; measure SDR on test set | TC-REQ-F-23-03
BUG-040 | F5.5 | Layered watermarks on stems | Low | Open | Watermark only the mix and the export bundle manifest; record stems in ledger | ADR-010; TD-04
BUG-041 | F6.1 | Certificate of ownership overstates rights | Launch-blocking | Partly resolved | Certificate states transfer of BeatMind's rights; never claims copyright exists | REQ-F-22; REQ-F-26
BUG-042 | F6.2 | Licensor terms may restrict output use | Launch-blocking | Resolved for now | No licensors in Phase 1; model licences checked (C-02) | ADR-007
BUG-043 | F6.3 | Subscribe; bulk download; charge back | Launch-blocking | Open | Paid ownership vests only for songs created while payment settled; chargeback revokes ownership of songs created in the disputed period | REQ-F-57
BUG-044 | F6.4 | Free-song upgrade has no price or rules | Medium | Open | Rule and price in Batch 4 | REQ-F-24
BUG-045 | F6.5 | Access after cancellation undefined | Medium | Open | Owned songs stay downloadable after cancellation (free-tier quotas apply to new creation) | REQ-F-58
BUG-046 | F7.1 | Authorship report certifies false human input | Launch-blocking | Open | Report says inputs are user-declared; no originality certification; terms make users warrant their inputs | REQ-F-31; Batch 4 legal pack
BUG-047 | F7.2 | Single signing key; 24-hour anchoring window | High | Open | Key in managed KMS; rotation; hourly digest | REQ-SEC-07; ADR-010
BUG-048 | F7.3 | Watermark not robust to adversarial removal | High | Open | Layered provenance; robustness test suite; never treat watermark absence as proof | TD-04
BUG-049 | F7.4 | Watermark presence proves only partial use | High | Open | Verify page reports match coverage and take; certificate tied to the full file hash | REQ-F-32
BUG-050 | F7.5 | Provenance retention versus erasure | Medium | Open | DPIA decision: keep pseudonymous ledger with legal-claims basis; counsel to confirm | dpia.md
BUG-051 | F8.1 | Distributor acceptance of disclosure | High | Deferred | Release pipeline is Phase 2 | FEAT-22
BUG-052 | F8.2 | Verify page is a free oracle | High | Open | Rate limits; Turnstile; file size cap; coarse answers to anonymous users | REQ-SEC-10
BUG-053 | F8.3 | Verify page leaks unreleased song metadata | Medium | Open | Show details only for public songs or to the certificate holder | REQ-F-32
BUG-054 | F9.1 | No Content ID clearance lever | Launch-blocking | Resolved | No clearance promised; dispute pack only | FEAT-11
BUG-055 | F9.2 | Channel OAuth scopes undefined | High | Deferred | No channel linking in MVP | Phase 2 backlog
BUG-056 | F9.3 | Licence scope for networks and reuploads undefined | Medium | Open | Define in licence terms | Batch 4 legal pack
BUG-057 | F10.1 | Voice verification can be spoofed | Launch-blocking | Deferred | Voice models removed from MVP | FEAT-30
BUG-058 | F10.2 | Protected-voice registry undefined | High | Deferred | With FEAT-30 | FEAT-30
BUG-059 | F10.3 | Biometric consent mechanics | High | Deferred | With FEAT-30 | FEAT-30
BUG-060 | F10.4 | Deleted voice model breaks songs | Medium | Deferred | With FEAT-30 | FEAT-30
BUG-061 | F10.5 | Account takeover exposes voice | High | Deferred | With FEAT-30 | FEAT-30
BUG-062 | F11.1 | Upload fingerprinting evadable | Launch-blocking | Deferred | No uploads in MVP | FEAT-21
BUG-063 | F11.2 | Similarity thresholds untuned | High | Open | Build labelled test set; set false-positive and false-negative targets before beta | TD-03; TC-REQ-F-52-01
BUG-064 | F11.3 | Similarity index coverage too narrow | High | Open | Choose reference index source | TD-03
BUG-065 | F11.4 | Moderation not multilingual | High | Open | Multilingual moderation incl. Devanagari and romanised Hindi; transliteration-aware artist list | REQ-F-51; REQ-SEC-04
BUG-066 | F11.5 | No appeal path | Medium | Open | Appeal button and human review queue in admin | REQ-F-59
BUG-067 | F12.1 | Insecure direct object references | Launch-blocking | Open | Owner-based authorisation on every resource; random non-sequential IDs; tests | REQ-SEC-02
BUG-068 | F12.2 | Private links never expire | High | Open | Revocable share tokens; signed URLs expire in 15 minutes | REQ-SEC-03
BUG-069 | F12.3 | Public page abuse | Medium | Open | Moderate titles and lyrics before publishing; link stripping; report button | REQ-F-50; REQ-F-51
BUG-070 | F12.4 | Search assumes Latin text | Medium | Open | Unicode-aware search with transliteration | REQ-NFR-09
BUG-071 | F13.1 | No entitlement matrix | Launch-blocking | Resolved | Entitlement matrix created | entitlement-matrix.csv
BUG-072 | F13.2 | No user MFA | High | Open | Optional TOTP or passkey; required for admins | REQ-SEC-06
BUG-073 | F13.3 | Age gate without verification; DPDP parental consent | High | Open | 18+ only in India for beta; parental-consent flow before allowing under-18s | REQ-F-53
BUG-074 | F13.4 | Card-only payments | High | Resolved | Razorpay with UPI in India | ADR-009
BUG-075 | F13.5 | No fraud controls on credits | Medium | Open | Provider fraud tools; velocity limits | REQ-SEC-09
BUG-076 | F14.1 | GPU time per job assumed | Launch-blocking | Open | Benchmark in Sprint 1; cost alert | A-025; REQ-NFR-07
BUG-077 | F14.2 | GPU supply for scale-up assumed | High | Open | Multi-provider worker images; API fallback with cap | ADR-006; ADR-007
BUG-078 | F14.3 | Fingerprint vendor rate limits | High | Open | Self-hosted fingerprinting; async screening queue | INT-08
BUG-079 | F14.4 | Merkle root growth | Medium | Resolved | Per-song chains plus daily signed digest of changed songs only | ADR-010
BUG-080 | F14.5 | No South Asia region | High | Resolved | India-first hosting region | TDD 1
BUG-081 | F14.6 | No load shedding for verify and public pages | Medium | Open | Separate rate limits and CDN caching; shed verify before generation | REQ-SEC-10
BUG-082 | L1 | Indic text length and normalisation | High | Open | Count grapheme clusters; store UTF-8 NFC; bidi support; embed fonts in PDFs | REQ-F-08
BUG-083 | L2 | Moderation not multilingual | Launch-blocking | Open | Same as F11.4; native-speaker review queue | REQ-F-51
BUG-084 | L3 | Singing pronunciation per language | High | Open | Language gate G1 per language | PRD 12
BUG-085 | L4 | Western music theory assumptions | High | Deferred | Indic music engine in Phase 3 (U7) | Phase 3 backlog
BUG-086 | L5 | No regional training data | High | Open | Model choice and G1; licensed regional data after funding | RISK-003; FEAT-33
BUG-087 | L6 | Cultural and legal content rules by market | High | Open | Per-market content policy reviewed by local counsel | compliance-register.csv
BUG-088 | L7 | US-centric payments | High | Resolved | ADR-009 and PPP pricing | ADR-009; DEC-013
BUG-089 | L8 | Lyric model quality per language | Medium | Open | Per-language lyric test | TD-01
BUG-090 | L9 | Metadata needs scripts and transliteration | Medium | Open | Store title in original script plus transliteration and language code | REQ-F-08

## Compliance
id | jurisdiction | instrument | obligation_summary | applies_to_beatmind_when | beta_status | evidence | source | implementing_controls | counsel_review
COMP-IN-01 | India | Information Technology Act 2000 s.79 and IT (Intermediary Guidelines and Digital Media Ethics Code) Rules 2021 | Safe-harbour due diligence: publish terms, privacy policy and user rules; appoint a grievance officer; acknowledge and resolve user complaints within set timelines; act on lawful orders | BeatMind hosts user content (public song pages) for Indian users | Likely applies | Assumption | Analyst knowledge; verify with counsel | REQ-F-54; REQ-F-59; Batch 4 legal pack | Required
COMP-IN-02 | India | IT Rules amendments on synthetically generated information (notified 2026-02-10; in force 2026-02-20) | Prominently label synthetic audio; embed permanent metadata or provenance markers with unique identifiers; do not allow markers to be removed; deploy technical measures against prohibited synthetic content; act on government or court orders within 3 hours | BeatMind offers tools that generate synthetic audio for Indian users | Applies | Externally sourced | SRC-117 | REQ-F-30; REQ-F-33; REQ-F-54; ADR-010 | Required: confirm label format for audio
COMP-IN-03 | India | IT Rules: significant social media intermediary duties | Additional duties incl. user declaration and verification of synthetic content | Only above 5 million registered users in India | Not yet | Externally sourced | SRC-117 | Monitor user count | Before threshold
COMP-IN-04 | India | Digital Personal Data Protection Act 2023 and DPDP Rules 2025 (notified November 2025; phased over 12 to 18 months) | Notice and consent; verifiable parental consent for children (under 18); reasonable security safeguards; breach intimation to the Board and affected users; erasure and retention limits; grievance redress; penalties up to ₹250 crore per breach | Processing personal data of users in India | Applies (phase dates to confirm, C-07) | Externally sourced (rules, penalty); Assumption (child age definition) | SRC-118 | REQ-F-53; REQ-NFR-05; dpia.md; consent table (TDD 5.1) | Required
COMP-IN-05 | India | Copyright Act 1957; DPIIT working paper on generative AI and copyright (December 2025, under consultation) | Avoid infringing outputs; authorship of computer-generated works rests with the person who causes the work to be created (s.2(d)(vi)) [to confirm]; AI training exceptions unsettled | All generated outputs and model use | Applies | Externally sourced (working paper); Assumption (s.2(d)(vi) reading) | SRC-102 | REQ-F-22; REQ-F-26; REQ-F-52; RISK-001; RISK-011 | Required
COMP-IN-06 | India | Consumer Protection Act 2019; Consumer Protection (E-Commerce) Rules 2020; Guidelines on dark patterns (2023) | Clear seller details and prices incl. taxes; grievance officer; no subscription traps or drip pricing; easy cancellation | Selling subscriptions to Indian consumers | Applies at paid launch | Assumption | Analyst knowledge; verify with counsel | REQ-F-40; REQ-F-43; UX spec section 6 | Required
COMP-IN-07 | India | Goods and Services Tax | Register; charge GST on subscriptions (Suno's Indian prices include 18% GST, SRC-111); file returns | Indian entity selling to Indian users | Applies at paid launch | Assumption (rate cross-checked against SRC-111) | SRC-111 | Financial model (Batch 4) | Required (tax adviser)
COMP-IN-08 | India | RBI framework for e-mandates on recurring card and UPI payments | Additional factor of authentication at mandate set-up; pre-debit notification; limits above which each charge needs authentication | Recurring subscription charges in India | Applies at paid launch | Assumption | Analyst knowledge; handled largely by the payment provider | ADR-009; INT-09 | Confirm with Razorpay
COMP-IN-09 | India | Personality and publicity rights (case law) | Do not imitate the voice, name or likeness of identifiable persons without consent; Indian courts have granted injunctions to performers against AI voice imitation [to confirm cases] | Prompts naming artists; voice features | Applies | Assumption | Analyst knowledge; verify with counsel | REQ-F-50; FEAT-30 deferred | Required
COMP-IN-10 | India | Companies Act 2013; foreign investment rules (FEMA) for fundraising | Incorporation, statutory filings; compliant issue of shares to foreign investors | If founders incorporate in India (A-001) | Pending Q-F01 | Assumption | A-001 | Batch 4 diligence pack | Required (company secretary)
COMP-EU-01 | European Union | AI Act Article 50 (applies from 2026-08-02; watermark sub-obligation runway to 2026-12-02) | Providers of systems generating synthetic audio must mark outputs in a machine-readable, detectable format; deployers must disclose deepfakes; fines up to €15M or 3% of turnover | Placing the generator on the EU market or serving EU users | Applies before serving EU users | Externally sourced | SRC-119 | ADR-010; C-06 | Required before Wave 3
COMP-EU-02 | European Union | General Data Protection Regulation | Lawful basis, transparency, data subject rights, DPIA where high risk, EU representative if no EU establishment, transfer safeguards | Offering services to people in the EU | Applies before serving EU users | Assumption | Analyst knowledge; verify with counsel | dpia.md; REQ-NFR-05 | Required before Wave 3
COMP-EU-03 | European Union | Digital Services Act | Notice-and-action for illegal content, statements of reasons, points of contact; lighter duties for micro and small enterprises | Hosting user content for EU users | Applies before serving EU users | Assumption | Analyst knowledge; verify with counsel | REQ-F-54; REQ-F-59 | Required before Wave 3
COMP-EU-04 | European Union | Consumer law on digital content and VAT | Withdrawal-right rules for digital content; VAT on digital services (merchant of record handles VAT collection) | Selling to EU consumers | Applies before paid EU sales | Assumption | Analyst knowledge | ADR-009 | Required before Wave 3
COMP-US-01 | United States | Copyright Office guidance (Part 2 report, 2025-01-29) | Purely AI-generated material is not protected; human expressive contributions, selection and arrangement may be | US users registering works | Applies (information duty to users) | Externally sourced | SRC-120 | REQ-F-26; authorship report wording | Required
COMP-US-02 | United States | DMCA s.512 safe harbour | Designate an agent with the Copyright Office; notice-and-takedown; repeat-infringer policy | Hosting user content accessible in the US | Likely applies | Assumption | Analyst knowledge | REQ-F-54 | Recommended
COMP-US-03 | United States | State right-of-publicity and voice laws | Do not commercially imitate a person's voice or likeness without consent | Voice and artist imitation | Applies | Assumption | Analyst knowledge | REQ-F-50 | Recommended
COMP-US-04 | United States | Children's Online Privacy Protection Act | Parental consent before collecting data from under-13s | Only if under-13s use the service | Not applicable in beta (18+ only) | Assumption | REQ-F-53 | REQ-F-53 | No
COMP-GL-01 | Global | Model licences (ACE-Step MIT or Apache-2.0; Stability Community Licence; Lyria API terms) | Keep licence and notice files; respect revenue thresholds and use restrictions | Using third-party models | Applies | Source-stated | SRC-105; SRC-106; SRC-108 | model-register.md; C-02 | Required
COMP-GL-02 | Global | Open-source licences of dependencies | Meet attribution and copyleft obligations (for example LGPL linking terms) | Shipping software with open-source components | Applies | Assumption | Analyst knowledge | CI licence scan (testing strategy section 6) | No
COMP-GL-03 | Global | Payment Card Industry Data Security Standard | Keep card data out of BeatMind systems; hosted checkout keeps scope minimal | Taking card payments | Applies at paid launch | Assumption | Analyst knowledge | ADR-009 | No
COMP-GL-04 | Global | Sanctions regimes | Block sanctioned regions and persons from paid services | Selling internationally | Applies at paid launch | Assumption | RISK-012; A-023 | Geo-blocking at checkout | Required
COMP-GL-05 | Global | Distributor and platform AI policies (YouTube; DistroKid; Spotify) | Disclose AI use; follow upload rules | Users releasing songs | Phase 2 | Unknown | C-05 | FEAT-22 | No
COMP-SA-01 | Pakistan; Bangladesh; Nepal | Local cybercrime, content and data laws | Unknown until local counsel review | Wave 2 launch | Not yet | Unknown | None | Wave 2 gate | Required before Wave 2

## RTM
requirement | feature | test_case | description | level | tool | automated | gate | status
REQ-F-01 | FEAT-01 | TC-REQ-F-01-01 | Description prompt returns two playable takes | E2E | Playwright | Yes | G2 | Not written
REQ-F-01 | FEAT-01 | TC-REQ-F-01-02 | p95 time to playable under 60 s at beta load | Performance | k6 | Yes | G2 | Not written
REQ-F-02 | FEAT-02 | TC-REQ-F-02-01 | Accepts 3,000 grapheme clusters of Devanagari; rejects 3,001 | Unit | JUnit 5 | Yes | G2 | Not written
REQ-F-02 | FEAT-02 | TC-REQ-F-02-02 | Hinglish and English lyrics accepted; vocal type and instrumental toggle honoured | Integration | JUnit 5 + Testcontainers | Yes | G2 | Not written
REQ-F-03 | FEAT-03 | TC-REQ-F-03-01 | Lyric writer returns verse, chorus and bridge sections in requested language | Integration | pytest | Yes | G1 | Not written
REQ-F-03 | FEAT-03 | TC-REQ-F-03-02 | Native-speaker review of 50 lyric samples per language | Manual | Review sheet | No | G1 | Not written
REQ-F-04 | FEAT-04 | TC-REQ-F-04-01 | Beat request validates BPM 60-200, key and instrument lists | Unit | JUnit 5 | Yes | G1 | Not written
REQ-F-04 | FEAT-04 | TC-REQ-F-04-02 | Detected tempo within ±3 BPM and key matches in target share of takes | Model eval | pytest + librosa | Yes | G1 | Not written
REQ-F-05 | FEAT-05 | TC-REQ-F-05-01 | Two takes per request; keep, regenerate and discard work | E2E | Playwright | Yes | G2 | Not written
REQ-F-06 | FEAT-02 | TC-REQ-F-06-01 | Lengths 30 s and 4 min produced within ±5 s | Model eval | pytest | Yes | G2 | Not written
REQ-F-07 | FEAT-16 | TC-REQ-F-07-01 | Language not passed G1 is hidden or marked experimental | Integration | JUnit 5 | Yes | G2 | Not written
REQ-F-08 | FEAT-16 | TC-REQ-F-08-01 | Text stored NFC; grapheme counting; transliteration and language tag stored | Unit | JUnit 5 | Yes | G2 | Not written
REQ-F-08 | FEAT-16 | TC-REQ-F-08-02 | Certificate PDF renders Devanagari correctly | Integration | JUnit 5 + PDF text extraction | Yes | G2 | Not written
REQ-F-10 | FEAT-06 | TC-REQ-F-10-01 | Extend, trim, fade and section regenerate create new versions | Integration | JUnit 5 | Yes | G2 | Not written
REQ-F-10 | FEAT-06 | TC-REQ-F-10-02 | Seam test: no onset or spectral discontinuity above threshold at edit boundaries | Model eval | pytest | Yes | G2 | Not written
REQ-F-11 | FEAT-06 | TC-REQ-F-11-01 | Compare and restore earlier version | E2E | Playwright | Yes | G2 | Not written
REQ-F-20 | FEAT-07 | TC-REQ-F-20-01 | Free MP3 192 kbps download carries attribution metadata | Integration | JUnit 5 | Yes | G2 | Not written
REQ-F-21 | FEAT-09 | TC-REQ-F-21-01 | Sixth commercial licence in a calendar month is refused | Unit | JUnit 5 | Yes | G2 | Not written
REQ-F-21 | FEAT-09 | TC-REQ-F-21-02 | Counter resets at month boundary in user's billing time zone | Unit | JUnit 5 | Yes | G2 | Not written
REQ-F-22 | FEAT-09 | TC-REQ-F-22-01 | Paid-plan song created with user_owned state and certificate wording approved by counsel | Integration | JUnit 5 | Yes | G3 | Not written
REQ-F-23 | FEAT-07 | TC-REQ-F-23-01 | Paid user downloads WAV 48 kHz 24-bit and MP3 320 | Integration | JUnit 5 | Yes | G2 | Not written
REQ-F-23 | FEAT-07 | TC-REQ-F-23-02 | Four stems produced and sum to mix within tolerance | Model eval | pytest | Yes | G2 | Not written
REQ-F-23 | FEAT-07 | TC-REQ-F-23-03 | Stem separation quality (SDR) reported on test set | Model eval | pytest | Yes | G2 | Not written
REQ-F-24 | FEAT-09 | TC-REQ-F-24-01 | Free song conversion rule applied (after Batch 4 rule) | Unit | JUnit 5 | Yes | G3 | Not written
REQ-F-25 | FEAT-09 | TC-REQ-F-25-01 | Cancelling does not change rights_status of existing songs | Unit | JUnit 5 | Yes | G2 | Not written
REQ-F-26 | FEAT-09 | TC-REQ-F-26-01 | Copy check: no string promises copyright protection or claim-free use | Static | Copy lint script | Yes | G2 | Not written
REQ-F-30 | FEAT-10 | TC-REQ-F-30-01 | Exported files carry AI label metadata, valid C2PA manifest and detectable watermark | Integration | pytest + c2patool | Yes | G2 | Not written
REQ-F-31 | FEAT-10 | TC-REQ-F-31-01 | Every generation, edit and export appends a ledger event; chain verifies | Unit | JUnit 5 | Yes | G2 | Not written
REQ-F-31 | FEAT-10 | TC-REQ-F-31-02 | Tampered event breaks chain verification | Unit | JUnit 5 | Yes | G2 | Not written
REQ-F-32 | FEAT-10 | TC-REQ-F-32-01 | Verify page identifies BeatMind file and reports coarse answer to anonymous users | E2E | Playwright | Yes | G2 | Not written
REQ-F-33 | FEAT-10 | TC-REQ-F-33-01 | AI-generated label visible on song page, embed and download dialog | E2E | Playwright | Yes | G2 | Not written
REQ-F-40 | FEAT-08 | TC-REQ-F-40-01 | Price shown in local currency for each band country | Unit | JUnit 5 | Yes | G3 | Not written
REQ-F-41 | FEAT-08 | TC-REQ-F-41-01 | Billing country of payment method overrides browsing country | Integration | JUnit 5 | Yes | G3 | Not written
REQ-F-42 | FEAT-08 | TC-REQ-F-42-01 | UPI, card and net banking checkout in Razorpay test mode | Integration | JUnit 5 + provider sandbox | Yes | G3 | Not written
REQ-F-43 | FEAT-08 | TC-REQ-F-43-01 | Cancellation completes in three steps or fewer | E2E | Playwright | Yes | G3 | Not written
REQ-F-50 | FEAT-14 | TC-REQ-F-50-01 | Artist names in Latin, Devanagari and romanised Hindi blocked | Unit | JUnit 5 | Yes | G2 | Not written
REQ-F-50 | FEAT-14 | TC-REQ-F-50-02 | Unicode attack corpus does not bypass block | Unit | JUnit 5 | Yes | G2 | Not written
REQ-F-51 | FEAT-14 | TC-REQ-F-51-01 | Lyric moderation red-team set in three languages: no prohibited output passes | Model eval | pytest | Yes | G2 | Not written
REQ-F-52 | FEAT-14 | TC-REQ-F-52-01 | Similarity screen withholds known near-copies in labelled set at target rates | Model eval | pytest | Yes | G2 | Not written
REQ-F-53 | FEAT-15 | TC-REQ-F-53-01 | Under-18 date of birth blocks sign-up | Unit | JUnit 5 | Yes | G2 | Not written
REQ-F-54 | FEAT-18 | TC-REQ-F-54-01 | Takedown disables song and notifies user; 3-hour order path works end to end | E2E | Playwright | Yes | G2 | Not written
REQ-F-55 | FEAT-17 | TC-REQ-F-55-01 | Daily cap and concurrency limit enforced per plan | Integration | JUnit 5 | Yes | G2 | Not written
REQ-F-56 | FEAT-08 | TC-REQ-F-56-01 | Failed, timed-out and withheld takes refund credits with ledger entry | Integration | JUnit 5 | Yes | G2 | Not written
REQ-F-57 | FEAT-09 | TC-REQ-F-57-01 | Chargeback webhook reverts rights of songs from the disputed period | Integration | JUnit 5 | Yes | G3 | Not written
REQ-F-58 | FEAT-09 | TC-REQ-F-58-01 | Cancelled user can still download owned songs | Integration | JUnit 5 | Yes | G3 | Not written
REQ-F-59 | FEAT-18 | TC-REQ-F-59-01 | Appeal creates review case visible in admin queue | E2E | Playwright | Yes | G2 | Not written
REQ-NFR-01 |  | TC-REQ-NFR-01-01 | Latency SLO measured under load profile | Performance | k6 | Yes | G2 | Not written
REQ-NFR-02 |  | TC-REQ-NFR-02-01 | Availability measured over 4 beta weeks | Monitoring | Grafana SLO | Yes | G3 | Not written
REQ-NFR-03 |  | TC-REQ-NFR-03-01 | Horizontal scale test: doubling API replicas roughly doubles throughput | Performance | k6 | Yes | G3 | Not written
REQ-NFR-04 |  | TC-REQ-NFR-04-01 | OWASP ASVS level 2 checklist completed | Manual | ASVS sheet | No | G3 | Not written
REQ-NFR-05 |  | TC-REQ-NFR-05-01 | Data export and deletion work end to end | E2E | Playwright | Yes | G2 | Not written
REQ-NFR-06 |  | TC-REQ-NFR-06-01 | No clipping; loudness of previews within ±1 LU of target | Model eval | pytest + pyloudnorm | Yes | G2 | Not written
REQ-NFR-07 |  | TC-REQ-NFR-07-01 | Cost per song metric emitted and alert fires above ceiling | Integration | JUnit 5 | Yes | G2 | Not written
REQ-NFR-08 |  | TC-REQ-NFR-08-01 | axe-core: zero serious or critical violations on all pages | Automated a11y | Playwright + axe-core | Yes | G2 | Not written
REQ-NFR-08 |  | TC-REQ-NFR-08-02 | Manual screen-reader pass (NVDA, TalkBack) on core flows | Manual | Checklist | No | G2 | Not written
REQ-NFR-09 |  | TC-REQ-NFR-09-01 | All UI strings externalised; Hindi locale renders without overflow | E2E | Playwright | Yes | G2 | Not written
REQ-NFR-10 |  | TC-REQ-NFR-10-01 | Core flows on a 3 GB RAM Android phone over throttled 4G | Manual | Device lab or emulator | No | G2 | Not written
REQ-SEC-01 |  | TC-REQ-SEC-01-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-02 |  | TC-REQ-SEC-02-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-03 |  | TC-REQ-SEC-03-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-04 |  | TC-REQ-SEC-04-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-05 |  | TC-REQ-SEC-05-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-06 |  | TC-REQ-SEC-06-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-07 |  | TC-REQ-SEC-07-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-08 |  | TC-REQ-SEC-08-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-09 |  | TC-REQ-SEC-09-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-10 |  | TC-REQ-SEC-10-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-11 |  | TC-REQ-SEC-11-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-12 |  | TC-REQ-SEC-12-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-13 |  | TC-REQ-SEC-13-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-14 |  | TC-REQ-SEC-14-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written
REQ-SEC-15 |  | TC-REQ-SEC-15-01 | See threat model section 5 verification column | Security | See threat-model.md | Yes | G2 | Not written

## Entitlements
entitlement | free | creator | pro | studio_phase2 | requirement
Song and beat generation | Daily cap set by admin | Monthly credits | Higher monthly credits | Team credits | REQ-F-01; REQ-F-55
Takes per request | 2 | 2 | 2 | 2 | REQ-F-05
Concurrent generation jobs | 1 | 2 | 4 | 8 | REQ-F-55
Song length | 30 s to 4 min | 30 s to 4 min | 30 s to 4 min | 30 s to 4 min | REQ-F-06
Languages | Launch languages that passed G1 | Same | Same | Same | REQ-F-07
AI lyric writer | Yes | Yes | Yes | Yes | REQ-F-03
Editor (extend; trim; fade; section regenerate) | Trim and fade only | Yes | Yes | Yes | REQ-F-10
MP3 download | 192 kbps personal use | 320 kbps | 320 kbps | 320 kbps | REQ-F-20; REQ-F-23
WAV download | No | Yes | Yes | Yes | REQ-F-23
Separated stems (vocals; drums; bass; other) | No | Yes | Yes | Yes | REQ-F-23
Commercial use | 5 songs per month with attribution (A-005) | All songs | All songs | All songs | REQ-F-21
Ownership of songs created on plan | BeatMind owns; user licensed | User owns | User owns | Organisation owns | REQ-F-22
Licence certificate | For the 5 licensed songs | Every song | Every song | Every song | FEAT-09
Dispute pack for claims | No | Yes | Yes | Yes | FEAT-11
Priority queue | No | No | Yes | Yes | PRD 9
Storage quota (kept takes) | 100 takes | 2000 takes | 10000 takes | Team pool | BUG-034
Public song page and embed | Yes | Yes | Yes | Yes | FEAT-13
Optional MFA | Yes | Yes | Yes | Required for admins | REQ-SEC-06
Team workspace and invoices | No | No | No | Yes | FEAT-24

## Backlog
id | epic | epic_name | story | acceptance_criteria | points | linked | target_sprint
US-001 | EP-01 | Foundations: repo, CI, environments, observability | As a developer, I want a monorepo with Java, Python and web modules building in CI, so that every change is tested | CI runs unit tests, scans and RTM check on every pull request; main is protected | 5 | REQ-SEC-12 | SPRINT-00
US-002 | EP-01 | Foundations: repo, CI, environments, observability | As a developer, I want Docker Compose for local development with a CPU model stub, so that I can work without a GPU | `docker compose up` starts web, API, Postgres, Valkey, MinIO and stub worker; README documents it | 3 |  | SPRINT-00
US-003 | EP-01 | Foundations: repo, CI, environments, observability | As an operator, I want staging and production environments defined in OpenTofu, so that environments are reproducible | Plan and apply succeed from CI; secrets from vault | 5 | ADR-006; ADR-012 | SPRINT-00
US-004 | EP-01 | Foundations: repo, CI, environments, observability | As an operator, I want OpenTelemetry traces, metrics and logs with dashboards, so that I can see SLOs | Dashboards for latency, errors, queue depth, GPU use, cost per song | 5 | REQ-NFR-07 | SPRINT-01
US-005 | EP-03 | Generation pipeline | As the team, I want ACE-Step 1.5 benchmarked on a rented GPU, so that we know real time and cost per take | Report with seconds per take, VRAM, cost per take for 3 GPU types; licence file archived | 3 | A-025; C-02 | SPRINT-00
US-006 | EP-04 | Lyrics and languages | As the team, I want a Hindi and Hinglish quality spike, so that we know if the beachhead language works | 20 prompts per language generated and scored by 3 native speakers; go or fallback decision | 3 | A-021; RISK-003 | SPRINT-00
US-007 | EP-12 | Validation and growth (waitlist, interviews, listening tests) | As the founder, I want a waitlist page with local prices shown, so that we measure interest and price response | Page live in English and Hindi; sign-ups stored with consent; price variant recorded | 3 | H-001; H-004 | SPRINT-00
US-008 | EP-12 | Validation and growth (waitlist, interviews, listening tests) | As the founder, I want 20 creator interviews done with a script, so that demand hypotheses are tested | Interview notes in repository; synthesis against H-001 to H-005 | 3 | DEC-012 | SPRINT-01
US-009 | EP-02 | Identity and accounts | As a creator, I want to sign in with Google or an email code, so that I can start quickly | Sign-in works; sessions secure per REQ-SEC-01; 18+ check at sign-up | 5 | REQ-F-53; REQ-SEC-01 | SPRINT-01
US-010 | EP-02 | Identity and accounts | As a user, I want to choose English or Hindi, so that the app speaks my language | Locale switch persists; all MVP strings in both languages | 3 | FEAT-16; REQ-NFR-09 | SPRINT-03
US-011 | EP-02 | Identity and accounts | As a user, I want to export or delete my data, so that I control my information | Export JSON plus files; deletion per DPIA section 6 | 5 | REQ-NFR-05 | SPRINT-04
US-012 | EP-03 | Generation pipeline | As a creator, I want to describe a vibe and get two takes, so that I get music for my video | API-001 and API-002 with SSE; two takes delivered; p95 under 60 s in staging | 8 | REQ-F-01; REQ-F-05 | SPRINT-01
US-013 | EP-03 | Generation pipeline | As the system, I want a durable Postgres job queue with retries and dead-letter, so that jobs survive restarts | Jobs claimed with SKIP LOCKED; retry with backoff; dead-letter visible in admin | 5 | ADR-005 | SPRINT-01
US-014 | EP-03 | Generation pipeline | As a creator, I want to see my queue position and wait time, so that I know when my song is ready | Live region announces status; estimate within ±30% | 3 | UX-A11Y-15 | SPRINT-04
US-015 | EP-03 | Generation pipeline | As a producer, I want Beat mode with genre, BPM, key and instruments, so that I can make instrumentals | Validation per REQ-F-04; tempo check runs on output | 5 | REQ-F-04 | SPRINT-04
US-016 | EP-03 | Generation pipeline | As the system, I want a Lyria fallback with a daily spend cap, so that paid users still get songs when GPUs are busy | Fallback used only when routed; cap enforced; cost logged | 3 | ADR-007; REQ-SEC-09 | SPRINT-05
US-017 | EP-04 | Lyrics and languages | As an artist, I want to paste lyrics in Hindi, Hinglish or English, so that my words become a song | Grapheme counting; NFC; language tag stored; custom mode works | 5 | REQ-F-02; REQ-F-08 | SPRINT-02
US-018 | EP-04 | Lyrics and languages | As a creator, I want the AI to write lyrics from a topic and mood, so that I can make a song without writing | Sectioned lyrics in chosen language; moderation applied | 5 | REQ-F-03 | SPRINT-03
US-019 | EP-05 | Provenance, labelling and certificates | As the system, I want every event written to a hash-chained ledger, so that provenance is provable | Chain verification test passes; tamper test fails as expected | 5 | REQ-F-31; REQ-SEC-07 | SPRINT-02
US-020 | EP-05 | Provenance, labelling and certificates | As a user, I want my downloads labelled and watermarked with content credentials, so that they meet AI rules | AI label metadata, valid C2PA manifest, detectable watermark on every export | 8 | REQ-F-30; COMP-IN-02 | SPRINT-02
US-021 | EP-05 | Provenance, labelling and certificates | As anyone, I want to verify a file or certificate, so that I can check its origin | Verify page with rate limits and coarse anonymous answers | 5 | REQ-F-32; REQ-SEC-10 | SPRINT-05
US-022 | EP-06 | Library, player and sharing | As a creator, I want a library of my songs and takes, so that I can find my work | List, search (Unicode-aware), rename, delete | 5 | FEAT-12 | SPRINT-02
US-023 | EP-06 | Library, player and sharing | As a creator, I want an accessible player that shows lyrics and the AI label, so that everyone can use it | Keyboard operable; ARIA; lyrics shown; label visible | 5 | REQ-F-33; UX-A11Y-01 to 03 | SPRINT-02
US-024 | EP-06 | Library, player and sharing | As a creator, I want to share a private link or public page, so that others can hear my song | Revocable share tokens; public page with moderation of title and lyrics | 5 | FEAT-13; REQ-SEC-03 | SPRINT-04
US-025 | EP-07 | Rights, quotas and downloads | As a free user, I want to mark up to 5 songs a month for commercial use, so that I can use them in videos | Quota enforced; certificate issued; attribution text provided | 5 | REQ-F-21 | SPRINT-03
US-026 | EP-07 | Rights, quotas and downloads | As a user, I want to download MP3 (and WAV when paid), so that I can use my song | Signed URLs 15 min; formats by plan per entitlement matrix | 3 | REQ-F-20; REQ-F-23 | SPRINT-02
US-027 | EP-07 | Rights, quotas and downloads | As a user, I want failed or withheld takes refunded, so that I never pay for nothing | Automatic refund with ledger entry | 3 | REQ-F-56 | SPRINT-02
US-028 | EP-08 | Safety and moderation | As the platform, I want prompts and lyrics moderated in Hindi, Hinglish and English, so that harmful content is blocked | Red-team set passes; Unicode corpus passes; reasons shown | 8 | REQ-F-50; REQ-F-51; REQ-SEC-04 | SPRINT-03
US-029 | EP-08 | Safety and moderation | As the platform, I want generated audio screened for similarity, so that near-copies are withheld | Screen runs on every take; withheld takes logged and refunded | 8 | REQ-F-52 | SPRINT-03
US-030 | EP-08 | Safety and moderation | As the platform, I want bot defence and caps, so that free generation is not abused | Turnstile; daily caps; concurrency limits; velocity rules | 5 | REQ-F-55; REQ-SEC-09 | SPRINT-02
US-031 | EP-09 | Admin and takedowns | As an admin, I want a console for users, caps and the moderation queue, so that I can run the beta | Role-gated; MFA required; every action audited | 8 | FEAT-18; REQ-SEC-06 | SPRINT-03
US-032 | EP-09 | Admin and takedowns | As an admin, I want takedown and appeal workflows with deadline timers, so that we meet the 3-hour rule | Orders path tested end to end; appeals queue works | 5 | REQ-F-54; REQ-F-59 | SPRINT-04
US-033 | EP-10 | Payments and pricing | As a user, I want to see prices in my currency for my country, so that the price is fair where I live | Price bands applied by billing country | 3 | REQ-F-40; REQ-F-41 | SPRINT-05
US-034 | EP-10 | Payments and pricing | As an Indian user, I want to pay by UPI, card or net banking, so that I can subscribe | Razorpay test and live mode; webhooks verified | 8 | REQ-F-42; REQ-SEC-08 | SPRINT-05
US-035 | EP-10 | Payments and pricing | As an international user, I want to pay through a merchant of record, so that taxes are handled | Provider checkout; webhooks verified | 5 | ADR-009 | SPRINT-06
US-036 | EP-10 | Payments and pricing | As a paid user, I want ownership of songs I create, with a certificate, so that I can use them anywhere | user_owned state; certificate; vesting on settlement; chargeback rule | 5 | REQ-F-22; REQ-F-57 | SPRINT-05
US-037 | EP-10 | Payments and pricing | As a user, I want to cancel online easily and keep my owned songs, so that I trust the service | Three-step cancel; downloads still available | 3 | REQ-F-43; REQ-F-58 | SPRINT-05
US-038 | EP-11 | Editor and stems | As a creator, I want to extend, trim, fade and regenerate a section, so that I can fix a take | New version per edit; seam test passes | 8 | REQ-F-10; REQ-F-11 | SPRINT-05
US-039 | EP-11 | Editor and stems | As a producer, I want four separated stems, so that I can mix my song | Demucs stems; sum test; SDR reported | 5 | REQ-F-23 | SPRINT-06
US-040 | EP-12 | Validation and growth (waitlist, interviews, listening tests) | As the team, I want G1 listening tests run for Hindi, Hinglish and English, so that we know which languages launch | 30 listeners per language; results against pass mark | 5 | PRD 12 | SPRINT-03
US-041 | EP-12 | Validation and growth (waitlist, interviews, listening tests) | As the founder, I want an investor demo script and recording, so that fundraising can start | Five-minute demo of the beta flow on staging | 2 | A-003 | SPRINT-04
US-042 | EP-01 | Foundations: repo, CI, environments, observability | As the team, I want a load test and a security baseline scan before beta, so that gate G2 is met | k6 at 2x beta peak; ZAP baseline; findings triaged | 5 | REQ-NFR-01; REQ-SEC-12 | SPRINT-04
US-043 | EP-01 | Foundations: repo, CI, environments, observability | As the team, I want accessibility checks in CI and a manual screen-reader pass, so that WCAG 2.2 AA holds | axe-core in CI; manual pass recorded | 3 | REQ-NFR-08 | SPRINT-04